# Eco-Schools Action Plan

# School name: SULLIVAN PREP

Keep an eye on progress throughout the year, perhaps you could use a traffic light system

Eco-Schools Topics: OUTDOOR LEARNING, ENERGY, TRANSPORT

# Date range of this plan: Sept 2020-June 2023

# Our overall aim(s) for this Topic: OUTDOOR LEARNING

To increase the amount of time pupils experience and benefit from outdoor learning by improving the outdoor facilities and developing a Forest School programme on site

| Problem Statement | Actions that can address the problem | How will you target the problem? | Timescale | Did you achieve your target? | What improvements could be made in future? |
| --- | --- | --- | --- | --- | --- |
| Nothing to interact with outdoors so students and teachers not going outdoors for learning | Money spent on buying sculptures Art teacher consulted for ideas | Ask SUPPA for funding so Mr Campbell can install equipment Do Eco School outdoor learning surveys before and after lessons rolled out | June 22 | - planters installed so pupils can create own floral presentations - blackboard on P3 outer wall for pupils to draw on - noticeboard out up in Magic Garden for pupil work and posters to be added for display - portable easels in place for children to create own artwork | See if local craftsmen can come and do willow weaving sculptures to be installed in gardens |
| No physical climbing/play facilities outdoors so no development of gross motor skills | Buy equipment Source natural materials | Ask school and eco council for ideas from pupils of what they would like | June 21 | - Class set of logs purchased - In upper and lower garden, fallen trees cleared of branches so now trunks can be used to walk along - 2 platforms built for climbing onto | Investigate cost of natural material climbing equipment, but is there the space? |
| No fruit/veg grown on school grounds by pupils so not getting hands on experience of growing own food | Buy seeds Each class takes on a planter and maintains it Apply for free fruit trees | From WAU funds and SUPPA buy bulbs and seeds and allocate to each class to plant during Green Day Apply for free trees | Throughout 2021-22 | - planters built and located around KS1 playground and KS2 building - Eco Warriors planted spring bulbs in new SUPPA Wellness Garden - FS/KS1 planted vegetable seeds in planters | Develop a small fruit orchard on far side of the school bridge Source a site for a small greenhouse for indoor planting |
| No record of how many lessons are held in the school grounds | Photo evidence of tasks can be recorded on school website/in Parentmail/on Seesaw | - Use NIFSA website to log activities | Jan-Feb 23 | -new NIFSA website allows for a record of entry with photo evidence for each lesson undertaken on and offsite | Maintain this record of activities Continue to publish photos to school community and NIFSA as evidence of outdoor work done |

| Problem Statement | Actions that can address the problem | How will you target the problem? | Timescale | Did you achieve your target? | What improvements could be made in future? |
| --- | --- | --- | --- | --- | --- |
| No outdoor classroom/log circle area so nowhere to sit outdoors for wellbeing sessions | Ask Eco and School Council what they would like Create a clearing to put in a log circle Get more outdoor seating Research | - clear area beside school canteen - clear area in lower garden - install outdoor taps | June 21 | - FS/KS1 Magic Garden developed and officially opened in 2022 - SUPPA Wellness Garden officially opened – seating area, apple tree, planters - new FS/KS1 water play area created outside P3 classroom - class set of waterproof tarpaulins/picnic mats purchased for outdoor lessons | - Plans underway for a covered outdoor classroom in KS2’s lower garden 2023-24 |
| No lessons held in the school grounds so not developing awareness of biodiversity in our local area | Only on Green Day – investigate outdoor learning planning ideas Do audit of WAU subjects and see how they lend themselves to outdoor learning Ask pupils if they want to learn more outdoors | - FS develop outdoor play facilities - audit of WAU teaching to find links to outdoors - provide resources for weekly timetabled outdoor lessons by all staff - investigate Forest School leader training for staff member - do outdoor learning surveys with pupils - invite RSPB rep in for Big Schools Bird Watch - Set up Foundation Stage outdoor learning club | Mar 22 | - Magic Garden now has a range of outdoor play activity stations with bunkers for storing safely - outdoors weekly assembly and outdoors weekly lessons with P1/7 buddies using waterproof mats - Mrs Matthews attended training and qualified as Level 3 FS Leader - P7 attending offsite Forest School sessions at Mt Stewart & Glen Lyon - regular Forest School Friday lessons held - during COVID Forest School tasks set for home completion and photo evidence submitted - yes, pupils surveyed before and after period of outdoor learning - P4 class did birdwatch lessons with Karen Sheils RSPB officer (Jan 23) - Little Acorns Club weekly for P1&2 pupils | Maintain forest school lessons on and offsite Produce schemes of work for outdoor learning per key stage |

Our overall aim(s) for this Topic: TRANSPORT

To reduce congestion outside school, to increase numbers of children making healthy and sustainable travel choices to get to/from school, to develop further road and cycling safety awareness amongst pupils

| Problem Statement | Actions that can address the problem | How will you target the problem? | Timescale | Did you achieve your target? | What improvements could be made in future? |
| --- | --- | --- | --- | --- | --- |
| We do not know how many people travel to school in a sustainable manner so | Travel audits Check on SIMS | - Eco council carry out class travel audits from P5-7 | 2020-2022 | - Surveys showed an increase in those walking to school, cycling to school after safety programme and more provision for sustainable travel on school grounds | Audit whole school Provide scooter storage in FS/KS1 playground |
| There is nowhere dry and safe to store bikes or scooters | Get a bike rack Provide a dry place outside Loughead | - source range of bike racks - make space for storage under building overhang | Easter 2022 | - new bike rack installed outside Loughead’s P4 classroom - further storage space alongside rear of Loughead with rearrangement of sports storage bunkers | Scooter rack beside Dromkeen House for FS/KS1 pupils to use |
| There are not any regular events to promote walking/ cycling to school | Apply to be part of/supported by Sustrans Active Travel programme | - Ask Sustrans to come in and lead activities |  | - P6 Cycle Skills programme run by Sustrans March 22 - 2 teachers trained to deliver P7 cycling proficiency programme May-June 22 - Take part in Sustrans Big Walk & Wheel campaign Mar 23 | Further promotion of safe cycling and scooting to school through annual safety teaching and campaigns |
| It is unsafe to walk or cycle to school | Book safety sessions with Sustrans Active Travel programme | - Ask Sustrans to come in and do road cycling with P6 - do cycling proficiency club for P7 - apply for reduced speed limit outside school - run safety awareness campaign in school | 2021-22 | - Stay Bright Stay Seen campaign Oct 20 - Road Safety Week assembly, poster design campaign Nov 21 - Bike safety gear demo for classes Jan 21 - Dr Bike session on how to check bike March 22 - 20mph sped limit signs and lights erected outside school site Jan 22 | Continue with annual road safety and cycling training |
| Cars park at entrance to the school | Cars park at Spa Field and pupils/parents walk up, pupils cycle to school, cars turn off engines at gates | - run the No Idling campaign - encourage park and stride from Spafield - widen window for school drop-off/pickup times |  | - 8.15am Morning Club began to reduced traffic - 8.30-9.00 longer arrival/drop-off time window - staggered home time collection to reduce congestion - pupils ran No Idling campaign Mar 22 | Continue with staggered arrival / collection times Encourage further park & stride use |

# Our overall aim(s) for this Topic: ENERGY

To reduce spending and usage, to reduce environmental impact, to develop pupil awareness of sources of energy

| Problem Statement | Actions that can address the problem | How will you target the problem? | Timescale | Did you achieve your target? | What improvements could be made in future? |
| --- | --- | --- | --- | --- | --- |
| Taking energy sources for granted so there is a level of ignorance in how to conserve energy Heat escaping through open doors and windows – have to be open due to COVID | Keep doors and windows closed when classes not in use | Window and doors closed when classes not in use – eco monitors | Ongoing | - Yes after COVID restrictions lifted, doors and windows closed more often to retain heat and reduce energy usage | Remind staff/pupils that fire doors should always be closed |
| Lights, IWBs, ICT suite devices left on | Automatic lights Light monitors | Lights off/ICT suite shut down when classes not in use – eco monitors | Ongoing | - ICT monitors in each class session make sure devices set to sleep at end of day or are shut down at end of week/half term | More regular spot checks on lights etc |
| Lack of pupil awareness of how our energy is generated, how it affects environment | Assemblies and workshops on energy sources and to encourage switching off devices not in use | Switch Off Fortnight campaign – assembly | Nov 22 | - P5 rep went to visit local business and gave presentation on how to save energy in the workplace | Can a teacher create a climate change focus in a weather topic? P4/7? |
| No one records electricity usage so noone aware of how much is wasted (financial capability) | Switch Off Fortnight campaign | Daily reading of electricity meters | Nov 22 | - P7 Eco monitors recorded usage each day for 2+ weeks - All eco monitors responsible for feedback to classes on how to - P7 class entered Switch Off Fortnight design competition | Create graphs to show the rise and fall of usage with this campaign in the future |
| No renewable energy onsite – no awareness of how to conserve/save | Develop education programme | Teaching climate change & renewable energy | Mar 23 | - P3 houses and homes topic – making homes energy efficient - P5 workshop on climate change - P6 lessons on electricity | Meet with SUS Facilities Manager about what can be installed on our Prep site |

This is a suggested addition to your Action Plan. For more information about the SDGs please visit www.eco-schoolsni.org “About Us” section.

# Which of the UN Sustainable Development Goals does our Eco-Schools Action Plan cover?

Circle at least one which we can link our Eco-Schools work to this year: