Topic	Action	Target / Measure	Timescale / Deadline	Responsibility	Actual result achieved / Date
General Eco School awareness and impact. / General Eco School awareness and impact. / General Eco School awareness and impact.	Set up a new Eco Committee	P4- 7 will hold elections to select first time representatives. Class Teacher to be involved with the choosing process.	New committee – 13/09/16	Miss Worthington	Eco Committee was established and welcomed. / New committee to be put on school website under heading 'Eco.' / New committee to be welcomed in Assembly and collect badges. New committee to be shared on parent mail.
	Eco Committee to conduct an Environmental Review.	Eco Committee to conduct an Environmental Review to identify an area of focus for Green Flag Award. / In pairs pupils will take an area of the Review to complete and share findings in an Eco Meeting. / Eco Committee to conduct follow up review.	First environmental review - September 2015 / September 2016	Miss Worthington	The Eco Committee splitting up to complete different sections of the Environmental Review worked well. The results of the Review were discussed at Eco Meeting. An additional meeting was held to discuss findings. The follow-up E.R was discussed also discussed.
	Create an Eco Code.	An Eco Code will be created highlighting the areas of focus for the Green Flag Award, reflecting the key elements from the Environmental Review	September	Eco Committee / ECO committee to type up and display in classrooms/ Eco board	On the 23rd September the Eco Council met to create an Eco Code focusing on what we were working on for the Green Flag Award.
	Create an Action Plan	Create an Action Plan with steps to follow on quest to Green Flag Award. / Action Plan to be put on School Website and Eco Board.	October 2016	Eco Committee / & Miss Worthington	An Action Plan was created and shared with pupils on 7th October 2016
	Scheduled Eco Meetings involving Eco Committee	Twice monthly, at least, agendas will displayed on board and meetings held. Eco Committee will take minutes put on Eco Board and School Website.	Twice monthly	Eco Committee	A copy is displayed on the Eco notice board.
	Make designated notice board	Maintain an Eco Committee Notice Board in a prominent area within the school	September 2016	Miss Worthington	Notice board has been positioned in Loughead House (outside P7 room)
	Have an area on school website	Regular updates, memos and photos will be put on school website to inform school community.	On-going	Mrs Matthews and Mrs Dempster	Area assigned on school website and updated by staff with recent minutes and photographs.
	Share Eco Code / Have in school days to raise awareness.	Eco Code will be shared within the whole school setting on the board, website and in assembly. Each class will also have a copy of the Eco Code displayed.	Autumn Term 2015 / Autumn Term	Eco Committee and Miss Worthington	Eco Code distributed to all classes- Sept 2015. / ‘Digital Detox Day’ carried out in November 2016. A great success, will be revisited in the next school year. / Switch Off poster posters made by P3and displayed around the school
	Increase publicity of Eco School within Press	When completing different campaigns photos and reports will be sent to newspaper.	On-going	Miss Worthington & Mrs Dempster / (depending on task)	Picture of new eco council sent to newspaper (Oct 2016) / Photographs of Eco Council with cash for clobber bags taken and sent to the local newspaper. (March 2017)

Topic	Action	Target / Measure	Timescale / Deadline	Responsibility	Actual result achieved / Date
Energy / Energy	To reduce energy consumption within the school by 10% / To reduce energy consumption within the school by 10%	Complete an expanded Energy Audit in addition to Environmental Review to find potential ways of saving energy.	On-going	Eco Committee& Miss Worthington	Information to be shared with Eco Council
		Complete an audit of what is on when the school is empty.	On-going	Mr Campbell & Miss Worthington	Information to be shared with Eco Council
		Monitor Energy Usage: / Out of hours – overnight / Daily consumption – over a week( record on bar chart) / Once a month (Record results in bar chart)	Summer Term / Out of hours, daily consumption. / Monthly times: / June, September, October, November, December	Nominate a person/ people to take responsibility for monitoring the energy consumption within the school over the above times. (Jake and Tara)	P7 Eco reps take readings for one week each month and then collate this data into tables and graphs to show energy consumption.
		‘Switch off when not in use’ signs to be located in each classroom next to lights.	Autumn Term 2016	Miss Worthington / Miss Cairnduff / P3 children	P3 children to design posters in WAU.
		Timetable to check computers at end of school day.	Daily / On-going	Miss Worthington & P7 Eco Committee members	Eco Council to report back
		Team to circulate classrooms at lunchtime to check lights are off. Interclass competition. Results to be displayed on Eco Notice Board. Results to be shared in Assembly at the end of each month.	Daily / On-going	Miss Worthington & Eco Committee	This took place over a 6 week period. Eco met every week to discuss findings and report back to other classes.
		Designated ‘Digital Detox Days’ per term within school and also encouraged at home.	November 2016	Miss Worthington	Digital Detox Days took place in November 2016
		Energy Saving tips displayed on Eco Board	November 2016	Eco Committee members

Topic	Action	Target / Measure	Timescale / Deadline	Responsibility	Actual result achieved / Date
Waste and Litter	Blue Bin Usage- / To minimise paper waste within each class through use of blue bins.	Each class will have a blue bin to collect paper waste in. A rota will be drawn up for Prep 7 children to empty these each day.	September 2016 onwards	Eco Committee	All results are recorded and displayed on the eco board.
	To minimise litter around the school grounds by having weekly litter pickers. / To take part in a litter pick/ beach clean-up (Wildlife watch) / All children are made aware of Recycling Week	Members of the Eco committee to litter pick at break and lunch time. All litter pickers will wear gloves and throw black bin bag into bigger black bins.	September 2016 onwards	Eco committee	P7 children to record how much litter is being collected and to sort
		Taking part in The Pod Waste Week	4 th – 10 th April / 2016/ / 6-10 March 2017	Whole school	All school took part and was a very successful week. Pictures on school website and Parent Mail sent home.
		Prep 7 children, Mrs Matthews and Mr Allen to clean up the local beach using gloves, litter pickers. All rubbish to be put into black bin bags and brought home to put in bigger black bins.	01/05/16	Prep 7 children	Picture evidence / pictures on website and ParentMail
		Green Day – June 2016 / Prep 5/ 3 to take part in a litter pick and survey. Children to record on template provided what they collected.	June 2016	Prep 3 and 5	Very successful – all photographs up on the website and on Friday ParentMail.
		Eco – Schools World Day of Action. Live Here Love Here. All children encouraged to take the pledge.	November 2nd - 6th November / 2016	Whole school	All classes given lesson plans and all extra information shared on Rm Staff. Children were able to share thoughts in Assembly.
		All children encouraged to take care when throwing out their rubbish this week. Posters updated to stick on blue bins. A staff room recycling poster is now stuck up for display. Staff is now more aware what they can recycle at lunch and break time.	(12th-16th September)	Whole school	A lot more rubbish in recycling blue bin this week. / All children shown short video on recycling.

Topic	Action	Target / Measure	Timescale / Deadline	Responsibility	Actual result achieved / Date
Biodiversity/ / School grounds	To make children more aware of our school grounds and what can be found in them.	Prep 1 and 7 went on a Green Day Nature walk.(June 2016) / Prep 2 went on a scavenger hunt.	June 2016 / Green Day	Whole school took part in Green Day	June 2016
	Prep 1 and Prep 4 make hedgehog homes with Karen from the RSPB.	We are wanting to develop our outdoor garden by using our outdoor camera to film animals that come into the garden. Children to work together with teachers to make hedgehog homes.	01/09/15	P1 and P4	We watched the camera footage back and we were able to identify a fox, dog, hedgehog and badger.
	Encourage children to be made aware of different birds found in our school grounds.	Throughout the year P4 will l record the types of birds they hear/ see in the school garden. Results will be sent away	2016	P4 and Eco ( Alex and Finn) designed posters for the eco board to make other children aware of the different types of birds we have in our school garden	Got a certificate from the RSPB for taking part in Big Schools' Birdwatch 2016
	Eco committee to meet and plant bulbs in the three beds. Children to plant daffodils, beans, peas and potatoes.	Children to meet throughout the year to weed, water and plant new bulbs in the three raised beds.	Spring 2016 / pick our potatoes in Sept 2016	Eco Committee, P4 and P3	Before we break for summer, children are able to see their bulbs grow and bloom. We will pick our potatoes in Sept 2016.
	ECO Committee to encourage children to put their fruit in the compost bin.		As soon as green bins arrive	Eco Committee 2015 / Mr Campbell
	Children to be made aware of living things in the garden	P4 children to go on a bug hunt and make bug hotels for Green Day	Green Day June 2016	P4 / Mrs Patterson	Children to look at their big hotel at the end of June.
	Using the free pea seeds from WWF campaign to plant in our school garden,	School registered to the WWF'S PLANT2PLATE CAMPAIGN	01/04/16	Eco Committee / Mrs Matthews	Children to plant pea seeds in Spring 2016 and pick them in September 2016